## Readiness Checklist
Critical Project Framework - Readiness Checklist *Please refer to the CPF Guideline to confirm the evidence requirements for the MCCP phase relevant to your CPF submission. **For customers providing additional collateral to meet the requirements of the next MCCP phase, only provide the new evidence specific to the phase the submission is being assesed against. There is no requirement to resubmit documentation previously provided for earlier phases.
Organisation Name: | Orgnisation
Project Name: | Project Number
Project Phase | Project Phase
Criteria | Sub-Criteria | Key Criteria | Description | Customer Supplied Document Name | Document Section Header / Page Number | Comments
Strategic Alignment | (3.1) Network Stability, Reliability & System Security & Location | Connection Type | Wind Farm, Solar, BESS, Gas, Hydrogen, Hybrid, Other Generation or Load
|  | Size Banding | <100MW 100- 249MW 250 - 500MW 500MW+
|  | Location | Future CEL Connection Connection to committed CEL or Terminal Connection to existing network Future build required Proven existing network capacity Proposed Project Location, Substation (if known) and Connection voltage requirements including Lat/Long co-ordinates (GIS Shape Files)
|  | Required in Service Dates Commercial Operational Date | Awareness of your RIS Dates and Commercial Operation Date.
|  | Existing Network Constraints (SAIDI / SAIFI) | If Customer has an awareness of Existing Network Constraints, please provide summary of proposed connection and solution.
|  | System or Government Initiative or Support | National Renewable Energy Priority List Lead Agency Framework WA State Government Committed Projects NCESS AEMO Reserves Capacity Certification and Capacity Investment Scheme Funded Projects Supplementary Reserve Capacity AEMO Electricity Statement of Opportunities (ESOO) / WEM
|  | Project Plan & Planned Activities | Please provide us with an overall project plan so we have an awareness of your project’s timing, activities & forecasted milestones. Formats accepted: Primavera (P6), MS Project or Schedule or Excel.
|  | Future Expansion (applicable where multiple projects are staged at the one location). | If applicable, please provide us with an awareness of future expansion including staging of projects either on foot or planned
|  | Point of Connection | If the customer knows the point of connection at the time of the CPF submission, or the distance from a Western Power connection point, please include this information in your submission. Additionally, please indicate whether there is flexibility in this connection point and if alternative connection locations would be considered.
| (3.2) Plans, Strategy & Policy Alignment | Stakeholder Consultation Project Alignment with National or State Government Policy or Strategy Project Alignment with Western Power's TXIP and NOM & Corporate Strategies | Stakeholder Consultation Alignment with National or State Government Policy or Strategy Alignment with TxIP, NOM or Corporate Strategies
Customer Readiness | (4.0) Customer Readiness | (4.1) Secured Land Access (Wind Farms) | Sufficient Evidence of Secured Land Access & Project Location Information Specfic for the phase the project is being assessed at.
|  | (4.2) Secured Land Access (Other Facilties) | Sufficient Evidence of Secured Land Access & Project Location for the phase the project is being assessed at.
|  | (4.3) Financial Readiness | Sufficient Evidence of Financial Readiness.
|  | (4.4) Procurement (assessed from Initiation onwards) | Sufficient Evidence of Procurement Documentation
|  | (4.5) Technical & Specialist Resources | RFP or SOW Documentation Capability Statements Emails or Letter of Engagement or Appointment
|  | (4.6) Social Performance | Sufficient Evidence of Social Performance Approach evidenced for the phase the project is being assessed at.
|  | (4.7) Environment & Herritage Approvals | Core Ennvironmental Approvals or Assessments Ecological & Heritage Surveys including timeline of plannned activities First Nations or Aboriginal Cultural Heritage Due Dilligence Assessment Supporting Plans and Engagement Environmental Studies and Survey Data
|  | (4.8) Previous Relevant Experience (evidence required once either at Enquiry or point of initial CPF submission) | Capability Statement
|  | (4.9) Risk Management | Overall Project Risk Summary
|  | (4.10) Connection Ability ( From initiation onwards) | Single Line Diagram (SLD) Steady State Power Factory Model
|  | Additional Project Information | This section is provided to enable customers to share any additional information they believe Western Power should consider in support of their CPF submission.
Readiness Declaration | (5.0) Readiness Declaration | (5.1) Readiness Checklist | Customer to include this Readiness Checklist in submission
|  | (5.2) Readiness Declaration | Readiness Declaration Signed Letter on Company Letterhead